## SDN-590
SDN-L590 Drilling Program | [5 empty] | As of : | 02/26/2021 | ON-GOING
[6 empty] | Time : | 0900H
Hole ID | PDH ID | PRS Northing | PRS Easting | PRS Elev | Dip (o) | Azimuth(o) | Rig type | Begin | End | Total days | Total Depth (m) | Status | Remarks
SDN2-590-001 | [6 empty] | DE-140 |  |  |  |  | Completed
SDN2-590-002 | [6 empty] | DE-140 |  |  |  |  | Completed
SDN2-590-003 | [6 empty] | DE-140 |  |  |  |  | Completed
SDN2-590-004 | [6 empty] | DE-140 | 2020-07-11 | 2020-08-15 | 36 | 400.3 | Completed
SDN2-590-005 | [6 empty] | DE-140 | 2020-08-15 | 2020-09-09 | 26 | 400.1 | Completed
SDN2-590-006 | [6 empty] | DE-140 | 2020-09-11 | 2020-10-03 | 23 | 421 | Completed
SDN2-590-007 | [6 empty] | DE-140 | 2020-10-05 | 2020-10-31 | 27 | 460.1 | Completed
SDN2-590-008 | [6 empty] | DE-140 | 2020-11-04 | 2020-11-28 | 25 | 475.1 | Completed
Running Total | [9 empty] | 137 | 2156.6
Proposed drilling meterage

## MAI-680
MAI-L680 Drilling Program | [5 empty] | As of : | 02/26/2021 | COMPLETED
[6 empty] | Time : | 0900H
Hole ID | PDH ID | PRS Northing | PRS Easting | PRS Elev | Dip (o) | Azimuth(o) | Rig type | Begin | End | Total days | Total Depth (m) | Status | Remarks
MAI-680-01 | [6 empty] | Diamec U6 | 2020-10-19 | 2020-11-09 | 22 | 482.5 | Completed
MAI-680-02 | [6 empty] | Diamec U6 | 2020-11-11 | 2020-11-26 | 16 | 500.8 | Completed
MAI-680-03 | [6 empty] | Diamec U6 | 2020-11-27 | 2020-12-10 | 14 | 404.9 | Completed
MAI-680-04 | [6 empty] | Diamec U6 | 2020-12-01 | 2020-12-27 | 27 | 415.7 | Completed
MAI-680-05 | [6 empty] | Diamec U6 | 2021-01-06 | 2021-01-21 | 16 | 458.7 | Completed | Hole deflected and intercepted active drive at L745
MAI-680-06 | [6 empty] | Diamec U6 | 2021-01-21 | 2021-02-09 | 20 | 560.4 | Completed
MAI-680-07 | [6 empty] | Diamec U6 | 2021-02-10 | 2021-02-23 | 14 | 440.1 | Completed
Running Total | [9 empty] | 129 | 3263.1
Proposed drilling meterage
-263.1

## WGS-500
WGS-L500 Drilling Program | [5 empty] | As of : | 02/26/2021 | ON-GOING
[6 empty] | Time : | 0900H
Hole ID | PDH ID | PRS Northing | PRS Easting | PRS Elev | Dip (o) | Azimuth(o) | Rig type | Begin | End | Total days | Total Depth (m) | Status | Remarks
WGS-500-001 | [6 empty] | Smart 4C | 2020-03-22 | 2020-07-11 |  | 370 | Completed
WGS-500-002 | [6 empty] | Smart 4C | 2020-07-11 | 2020-08-11 |  | 381.8 | Completed
WGS-500-003 | [6 empty] | Smart 4C | 2020-08-11 | 2020-09-07 |  | 297.3 | Completed
WGS-500-004 | [6 empty] | Smart 4C | 2020-09-08 | 2020-09-26 |  | 371 | Completed
WGS-500-005 | [6 empty] | Smart 4C | 2020-09-26 | 2020-10-13 |  | 381.3 | Completed
WGS-500-006 | [6 empty] | Smart 4C | 2020-10-13 | 2020-10-31 |  | 381.8 | Completed
WGS-500-007 | [6 empty] | Smart 4C | 2020-11-04 | 2020-11-21 |  | 382.9 | Completed
WGS-500-008 | [6 empty] | Smart 4C | 2020-11-24 | 2020-12-14 |  | 405.6 | Completed
WGS-500-009 | [6 empty] | Smart 4C | 2020-12-15 | 2021-01-16 |  | 395 | Completed
WGS-500-010 | [6 empty] | Smart 4C | 2021-01-18 | 2021-02-06 |  | 307.8 | Completed
WGS-500-011 | [6 empty] | Smart 4C | 2021-02-08 |  |  |  | On-going
Running Total | [9 empty] | 0 | 3674.5
Proposed drilling meterage

## DNM-530
WGS-L500 Drilling Program | [5 empty] | As of : | 02/26/2021 | ON-GOING
[6 empty] | Time : | 0900H
Hole ID | PDH ID | PRS Northing | PRS Easting | PRS Elev | Dip (o) | Azimuth(o) | Rig type | Begin | End | Total days | Total Depth (m) | Status | Remarks
DNM-530-01 |  |  |  |  | 2 | 150 | LM-90 | 2021-01-24 |  |  |  | On-going
Running Total | [9 empty] | 0 | 0
Proposed drilling meterage

## 2021 Drilling
Rig No. | January 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | February 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | March 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | April 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | May 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | June 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | July 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance
Rig No. | August 2021
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Meterage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mob = | Rig Mobilization |  |  | Main= | Maintenance

## Monthly Running Summary
Monthly monitoring | Proposed monthly drilling meterage | Actual monthly drilling meterage
January
February
March
April
May
June
July
August
September
October
November
December
Ave:
UG Drilling Meterage 2021
Area | Rig name | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec